## Sheet1
|  |  |  | October | [7 empty] | November | [6 empty] | December
Task Name | Day | Start | Finish | 1 | 4 | 7 | 8 | 9 | 10 | 15 | 25 | 5 | 11 | 12 | 17 | 18 | 19 | 28 | 31 | 1 | 8 | 9 | 15 | 20
Requirement Gathering and analysis
analysis current process | 3 | 1.10.2024 | 4.10.2024
define system requirement | 3 | 4.10.2024 | 7.10.2024
System Design and Development
design system atchitecture | 5 | 8.10.2024 | 15.10.2024
frond end development | 10 | 15.10.2024 | 25.10.2024
back end development | 15 | 25.10.2024 | 5.11.2024
Testing and quality assurance
test the system | 5 | 05.11.2024 | 11.11.2024
user accepting system | 1 | 11.11.2024 | 12.11.2024
Training and Documentation
prepare user documentation | 1 | 18.11.2024 | 19.11.2024
conduct training | 9 | 19.11.2024 | 28.11.2024
Deployement
deploy the system | 3 | 28.11.2024 | 31.11.2024
monitor the deployed system | 20 | 01.12.2024 | 20.12.2024